## All
University Outcomes (Performance Target/Metric) | Activity | Activity *Short* Name | RESPONSIBILITY | TIMELINE | RESPONSIBLE_PARTY
RA/RI Outcome 1: By the end of 2024-2025, EWU will finalize its decarbonization plan which will describe how the University will eliminate its greenhouse gas emissions and improve the University’s climate resilience. By the end of 2025-2026 the plan will be updated to describe how students, faculty and staff will be involved in plan development and implementation | Establish a cross-functional sustainability task force to develop and finalize a decarbonization plan that ensures involvement of students, faculty, and staff. (1) | Establish a cross-functional sustainability task force | VPBS / VPAA | 2024-2029 | VPAA
RA/RI Outcome 1: By the end of 2024-2025, EWU will finalize its decarbonization plan which will describe how the University will eliminate its greenhouse gas emissions and improve the University’s climate resilience. By the end of 2025-2026 the plan will be updated to describe how students, faculty and staff will be involved in plan development and implementation | Establish a cross-functional sustainability task force to develop and finalize a decarbonization plan that ensures involvement of students, faculty, and staff. (1) | Establish a cross-functional sustainability task force | VPBS / VPAA | 2024-2029 | VPBS
Belonging Outcome 6: Beginning in 2024, increase alumni engagement by 20% each year through various means of time (e.g., volunteerism on boards, etc.), talent (e.g., utilizing their profession), and treasures (e.g., giving), further, investing in an active alumni culture. | Expand alumni engagement through athletic and community events (on campus and off campus), career development, mentorship programs, volunteer opportunities, fundraising campaigns, professional expertise programs, regular events, and a recognition program to foster a vibrant alumni community. (6) | Expand alumni engagement through athletic and community events | VPUA/DOA | 2024-2027 | DOA
Belonging Outcome 6: Beginning in 2024, increase alumni engagement by 20% each year through various means of time (e.g., volunteerism on boards, etc.), talent (e.g., utilizing their profession), and treasures (e.g., giving), further, investing in an active alumni culture. | Expand alumni engagement through athletic and community events (on campus and off campus), career development, mentorship programs, volunteer opportunities, fundraising campaigns, professional expertise programs, regular events, and a recognition program to foster a vibrant alumni community. (6) | Expand alumni engagement through athletic and community events | VPUA/DOA | 2024-2027 | VPUA
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | Offer staff in service programs and an annual faculty retreat (1,5) | Offer staff in service programs and an annual faculty retreat | VPPC/VPAA | 2024-2029 | VPAA
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | Offer staff in service programs and an annual faculty retreat (1,5) | Offer staff in service programs and an annual faculty retreat | VPPC/VPAA | 2024-2029 | VPPC
IIPP Outcome 5: By 2026-2027, 100% of staff will participate in a professional development opportunity annually | Offer staff in service programs and an annual faculty retreat (1,5) | Offer staff in service programs and an annual faculty retreat | VPPC/VPAA | 2024-2029 | VPAA
IIPP Outcome 5: By 2026-2027, 100% of staff will participate in a professional development opportunity annually | Offer staff in service programs and an annual faculty retreat (1,5) | Offer staff in service programs and an annual faculty retreat | VPPC/VPAA | 2024-2029 | VPPC
RA/RI Outcome 3: By 2025-2026, EWU will complete a comprehensive regional economic profile using data-driven analytics and use that profile to promote academic offerings that benefit our region in preparation for the development of an academic master plan. | EWU will align its programmatic offerings with regional economic activities by identifying top in-demand jobs and their required skills, creating a catalog of these skills, and then updating existing programs or developing new ones to incorporate these skill sets. (3,4,6,7) | Align programmatic offerings with regional economic activities | VPAA | 2025-2029 | VPAA
RA/RI Outcome 4: By 2026-2027, 25% of the faculty will participate in community engagement activities, increasing to 75% by 2028-2029. | EWU will align its programmatic offerings with regional economic activities by identifying top in-demand jobs and their required skills, creating a catalog of these skills, and then updating existing programs or developing new ones to incorporate these skill sets. (3,4,6,7) | Align programmatic offerings with regional economic activities | VPAA | 2025-2029 | VPAA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | EWU will align its programmatic offerings with regional economic activities by identifying top in-demand jobs and their required skills, creating a catalog of these skills, and then updating existing programs or developing new ones to incorporate these skill sets. (3,4,6,7) | Align programmatic offerings with regional economic activities | VPAA | 2025-2029 | VPAA
RA/RI Outcome 7: By 2028-2029, EWU will develop a multi-year investment and change-management plan that coordinates major state and institutional infrastructure investments with the development of faculty, student, and community engagement programs. | EWU will align its programmatic offerings with regional economic activities by identifying top in-demand jobs and their required skills, creating a catalog of these skills, and then updating existing programs or developing new ones to incorporate these skill sets. (3,4,6,7) | Align programmatic offerings with regional economic activities | VPAA | 2025-2029 | VPAA
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | EWU will analyze faculty and staff turnover to develop, implement, and evaluate programs to improve recruitment and increase retention. (1,2) | Analyze faculty and staff turnover | VPBS/VPPC | 2025-2027 | VPBS
IIPP Outcome 2: Increase the recruitment of qualified applicants for all permanent EWU positions by 1% annually, and align employee demographics with the diversity of the EWU student population. | EWU will analyze faculty and staff turnover to develop, implement, and evaluate programs to improve recruitment and increase retention. (1,2) | Analyze faculty and staff turnover | VPBS/VPPC | 2025-2027 | VPBS
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Conduct a detailed analysis of the past five years to identify courses with high DFW rates and develop effective interventions and ongoing assessment of these courses. (1,2,4) | Analyze high DFW rate courses | VPAA | 2024-2029 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Conduct a detailed analysis of the past five years to identify courses with high DFW rates and develop effective interventions and ongoing assessment of these courses. (1,2,4) | Analyze high DFW rate courses | VPAA | 2024-2029 | VPAA
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Conduct a detailed analysis of the past five years to identify courses with high DFW rates and develop effective interventions and ongoing assessment of these courses. (1,2,4) | Analyze high DFW rate courses | VPAA | 2024-2029 | VPAA
Belonging Outcome 3: By 2026-2027, the number of students who participate in a university mentoring program or university support service will increase by 10% and participants will have a 10% greater outcome (measured by retention and graduation) than those who did not participate in a mentorship opportunity. | By the end of the 2027 academic year, EWU will establish a framework to effectively communicate, coordinate, support, track, and assess mentorship and university support service opportunities (3) | Assess mentorship and university support service opportunities | VPAA/VPSA | 2026-2028 | VPAA
Belonging Outcome 3: By 2026-2027, the number of students who participate in a university mentoring program or university support service will increase by 10% and participants will have a 10% greater outcome (measured by retention and graduation) than those who did not participate in a mentorship opportunity. | By the end of the 2027 academic year, EWU will establish a framework to effectively communicate, coordinate, support, track, and assess mentorship and university support service opportunities (3) | Assess mentorship and university support service opportunities | VPAA/VPSA | 2026-2028 | VPSA
Belonging Outcome 1: By 2025-2026, all university and academic policies, including those specific to individual units, will undergo an equity-minded audit to identify policies and practices contributing to inequitable outcomes for historically underrepresented students/faculty/staff. | Based on the audit findings, develop and implement comprehensive action plans to revise policies, promote inclusivity, and ensure equitable opportunities and outcomes for all students, faculty, and staff. (1,2) | Based on the audit findings, develop and implement comprehensive action plans | VPPC/ELT | 2026-2029 | ELT
Belonging Outcome 1: By 2025-2026, all university and academic policies, including those specific to individual units, will undergo an equity-minded audit to identify policies and practices contributing to inequitable outcomes for historically underrepresented students/faculty/staff. | Based on the audit findings, develop and implement comprehensive action plans to revise policies, promote inclusivity, and ensure equitable opportunities and outcomes for all students, faculty, and staff. (1,2) | Based on the audit findings, develop and implement comprehensive action plans | VPPC/ELT | 2026-2029 | VPPC
Belonging Outcome 2: By 2027-2028, all academic and student support units will implement equity-minded accountability and assessment practices and an annual reporting instrument that includes measures such as the participation and/or success rates of students disaggregated by race/ethnicity, socioeconomic status, and gender. | Based on the audit findings, develop and implement comprehensive action plans to revise policies, promote inclusivity, and ensure equitable opportunities and outcomes for all students, faculty, and staff. (1,2) | Based on the audit findings, develop and implement comprehensive action plans | VPPC/ELT | 2026-2029 | ELT
Belonging Outcome 2: By 2027-2028, all academic and student support units will implement equity-minded accountability and assessment practices and an annual reporting instrument that includes measures such as the participation and/or success rates of students disaggregated by race/ethnicity, socioeconomic status, and gender. | Based on the audit findings, develop and implement comprehensive action plans to revise policies, promote inclusivity, and ensure equitable opportunities and outcomes for all students, faculty, and staff. (1,2) | Based on the audit findings, develop and implement comprehensive action plans | VPPC/ELT | 2026-2029 | VPPC
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Conduct an inventory and needs assessment to enhance academic support services and develop opportunities, such as Supplemental Instruction, across the university. (1,2,3,4) | Conduct a needs assessment for student support services | VPAA | 2024-2026 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Conduct an inventory and needs assessment to enhance academic support services and develop opportunities, such as Supplemental Instruction, across the university. (1,2,3,4) | Conduct a needs assessment for student support services | VPAA | 2024-2026 | VPAA
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Conduct an inventory and needs assessment to enhance academic support services and develop opportunities, such as Supplemental Instruction, across the university. (1,2,3,4) | Conduct a needs assessment for student support services | VPAA | 2024-2026 | VPAA
SSE Outcome 4: By 2028-2029, decrease the DFW (Drop, Fail, and Withdrawal) rates in courses with historically high DFW rates and reduce the DFW rates for all courses to less than 20%. | Conduct an inventory and needs assessment to enhance academic support services and develop opportunities, such as Supplemental Instruction, across the university. (1,2,3,4) | Conduct a needs assessment for student support services | VPAA | 2024-2026 | VPAA
Belonging Outcome 2: By 2027-2028, all academic and student support units will implement equity-minded accountability and assessment practices and an annual reporting instrument that includes measures such as the participation and/or success rates of students disaggregated by race/ethnicity, socioeconomic status, and gender. | Create a directory of DEI experts across campus and a repository of DEI resources. (2,5) | Create a directory of DEI experts across campus | President's Office | 2024-2025 | President's Office
Belonging Outcome 5: By 2027-2028, all of EWU will have an improved sense of belonging by improved student journey mapping, onboarding, and training experiences to include surveys of satisfaction and exit interview feedback to increase sense of belonging for all. | Create a directory of DEI experts across campus and a repository of DEI resources. (2,5) | Create a directory of DEI experts across campus | President's Office | 2024-2025 | President's Office
RA/RI Outcome 2:By 2025-2026, EWU will develop a comprehensive brand and identity marketing plan that supports the future of the university. | Enhance EWU's brand recognition and reputation by creating a unified and compelling brand message that resonates with prospective students, alumni, and the community. (2) | Create a unified and compelling brand message | VPUA/DOA | 2024-2028 | DOA
RA/RI Outcome 2:By 2025-2026, EWU will develop a comprehensive brand and identity marketing plan that supports the future of the university. | Enhance EWU's brand recognition and reputation by creating a unified and compelling brand message that resonates with prospective students, alumni, and the community. (2) | Create a unified and compelling brand message | VPUA/DOA | 2024-2028 | VPUA
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | EWU will create an onboarding and training program that ensures new employees and those in new roles are integrated, understand their unit's goals, and have immediate access to essential resources and tools. (1,4) | Create an improved onboarding and training program | VPPC | 2025-2029 | VPPC
IIPP Outcome 4: Overall campus Climate Survey score will increase by 10% in 2027-2028 and meet or exceed other peer and national institutions. | EWU will create an onboarding and training program that ensures new employees and those in new roles are integrated, understand their unit's goals, and have immediate access to essential resources and tools. (1,4) | Create an improved onboarding and training program | VPPC | 2025-2029 | VPPC
Belonging Outcome 5: By 2027-2028, all of EWU will have an improved sense of belonging by improved student journey mapping, onboarding, and training experiences to include surveys of satisfaction and exit interview feedback to increase sense of belonging for all. | Create detailed student journey maps from admission to graduation using satisfaction surveys and using feedback to continuously refine policies and practices to foster a more inclusive and supportive environment. (5) | Create detailed student journey maps from admission to graduation | ELT | 2024-2029 | ELT
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | EWU will cultivate a community of practice that invests in a workplace culture that provides resources for the continuous learning and professional development of all employees. (1,5) | Cultivate a community of practice for the continuous learning and professional development of all employees | VPPC | 2024-2029 | VPPC
IIPP Outcome 5: By 2026-2027, 100% of staff will participate in a professional development opportunity annually | EWU will cultivate a community of practice that invests in a workplace culture that provides resources for the continuous learning and professional development of all employees. (1,5) | Cultivate a community of practice for the continuous learning and professional development of all employees | VPPC | 2024-2029 | VPPC
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Create a cross-divisional task force to develop and implement a Comprehensive Campus-Wide student Well-Being Program. (3) | Develop a comprehensive campus-wide student well-being program | VPSA | 2024-2027 | VPSA
RA/RI Outcome 3: By 2025-2026, EWU will complete a comprehensive regional economic profile using data-driven analytics and use that profile to promote academic offerings that benefit our region in preparation for the development of an academic master plan. | EWU will develop a joint urban planning framework with Cheney and the West Plains to align campus development with regional growth, fostering professional partnerships and student opportunities. (3,6) | Develop a joint urban planning framework with Cheney and the West Plain | VPAA / VPBS / VPSA | 2025-2027 | VPAA
RA/RI Outcome 3: By 2025-2026, EWU will complete a comprehensive regional economic profile using data-driven analytics and use that profile to promote academic offerings that benefit our region in preparation for the development of an academic master plan. | EWU will develop a joint urban planning framework with Cheney and the West Plains to align campus development with regional growth, fostering professional partnerships and student opportunities. (3,6) | Develop a joint urban planning framework with Cheney and the West Plain | VPAA / VPBS / VPSA | 2025-2027 | VPBS
RA/RI Outcome 3: By 2025-2026, EWU will complete a comprehensive regional economic profile using data-driven analytics and use that profile to promote academic offerings that benefit our region in preparation for the development of an academic master plan. | EWU will develop a joint urban planning framework with Cheney and the West Plains to align campus development with regional growth, fostering professional partnerships and student opportunities. (3,6) | Develop a joint urban planning framework with Cheney and the West Plain | VPAA / VPBS / VPSA | 2025-2027 | VPSA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | EWU will develop a joint urban planning framework with Cheney and the West Plains to align campus development with regional growth, fostering professional partnerships and student opportunities. (3,6) | Develop a joint urban planning framework with Cheney and the West Plain | VPAA / VPBS / VPSA | 2025-2027 | VPAA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | EWU will develop a joint urban planning framework with Cheney and the West Plains to align campus development with regional growth, fostering professional partnerships and student opportunities. (3,6) | Develop a joint urban planning framework with Cheney and the West Plain | VPAA / VPBS / VPSA | 2025-2027 | VPBS
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | EWU will develop a joint urban planning framework with Cheney and the West Plains to align campus development with regional growth, fostering professional partnerships and student opportunities. (3,6) | Develop a joint urban planning framework with Cheney and the West Plain | VPAA / VPBS / VPSA | 2025-2027 | VPSA
Belonging Outcome 5: By 2027-2028, all of EWU will have an improved sense of belonging by improved student journey mapping, onboarding, and training experiences to include surveys of satisfaction and exit interview feedback to increase sense of belonging for all. | Develop resources for university employees for successful onboarding and integration into university and community. (5) | Develop resources for successful onboarding | VPPC/President's Office | 2024-2025 | President's Office
Belonging Outcome 5: By 2027-2028, all of EWU will have an improved sense of belonging by improved student journey mapping, onboarding, and training experiences to include surveys of satisfaction and exit interview feedback to increase sense of belonging for all. | Develop resources for university employees for successful onboarding and integration into university and community. (5) | Develop resources for successful onboarding | VPPC/President's Office | 2024-2025 | VPPC
IIPP Outcome 3: By 2025-2026, EWU will develop a campus master plan, which will explicitly incorporate residence halls, and include a vision for both Cheney and Spokane locations. | Develop robust residential life plan including physical structure, programs and assessment. (3) | Develop robust residential life plan | VPSA/VPBS | 2024-2029 | VPBS
IIPP Outcome 3: By 2025-2026, EWU will develop a campus master plan, which will explicitly incorporate residence halls, and include a vision for both Cheney and Spokane locations. | Develop robust residential life plan including physical structure, programs and assessment. (3) | Develop robust residential life plan | VPSA/VPBS | 2024-2029 | VPSA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Develop and implement the strategic enrollment management plan. (1,2) | Develop strategic enrollment management plan | VPAA | 2024-2028 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Develop and implement the strategic enrollment management plan. (1,2) | Develop strategic enrollment management plan | VPAA | 2024-2028 | VPAA
RA/RI Outcome 4: By 2026-2027, 25% of the faculty will participate in community engagement activities, increasing to 75% by 2028-2029. | Enhance applied learning opportunities with specific fundraising for these student opportunities. (4,6,7) | Enhance applied learning opportunities | VPSA/VPUA | 2024-2027 | VPSA
RA/RI Outcome 4: By 2026-2027, 25% of the faculty will participate in community engagement activities, increasing to 75% by 2028-2029. | Enhance applied learning opportunities with specific fundraising for these student opportunities. (4,6,7) | Enhance applied learning opportunities | VPSA/VPUA | 2024-2027 | VPUA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | Enhance applied learning opportunities with specific fundraising for these student opportunities. (4,6,7) | Enhance applied learning opportunities | VPSA/VPUA | 2024-2027 | VPSA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | Enhance applied learning opportunities with specific fundraising for these student opportunities. (4,6,7) | Enhance applied learning opportunities | VPSA/VPUA | 2024-2027 | VPUA
RA/RI Outcome 7: By 2028-2029, EWU will develop a multi-year investment and change-management plan that coordinates major state and institutional infrastructure investments with the development of faculty, student, and community engagement programs. | Enhance applied learning opportunities with specific fundraising for these student opportunities. (4,6,7) | Enhance applied learning opportunities | VPSA/VPUA | 2024-2027 | VPSA
RA/RI Outcome 7: By 2028-2029, EWU will develop a multi-year investment and change-management plan that coordinates major state and institutional infrastructure investments with the development of faculty, student, and community engagement programs. | Enhance applied learning opportunities with specific fundraising for these student opportunities. (4,6,7) | Enhance applied learning opportunities | VPSA/VPUA | 2024-2027 | VPUA
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | Enhance faculty and staff well-being and resilience with a data-informed approach (1,4) | Enhance faculty and staff well-being | VPBS/VPAA | 2025-2027 | VPAA
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | Enhance faculty and staff well-being and resilience with a data-informed approach (1,4) | Enhance faculty and staff well-being | VPBS/VPAA | 2025-2027 | VPBS
IIPP Outcome 4: Overall campus Climate Survey score will increase by 10% in 2027-2028 and meet or exceed other peer and national institutions. | Enhance faculty and staff well-being and resilience with a data-informed approach (1,4) | Enhance faculty and staff well-being | VPBS/VPAA | 2025-2027 | VPAA
IIPP Outcome 4: Overall campus Climate Survey score will increase by 10% in 2027-2028 and meet or exceed other peer and national institutions. | Enhance faculty and staff well-being and resilience with a data-informed approach (1,4) | Enhance faculty and staff well-being | VPBS/VPAA | 2025-2027 | VPBS
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Establish an office of applied learning and community engagement to develop, coordinate, and promote internships, co-ops, service-learning, and undergraduate research in collaboration with academic departments, community partners, and employers. (1,2,5) | Establish an office of applied learning and community engagement | VPSA/VPAA | 2024-2027 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Establish an office of applied learning and community engagement to develop, coordinate, and promote internships, co-ops, service-learning, and undergraduate research in collaboration with academic departments, community partners, and employers. (1,2,5) | Establish an office of applied learning and community engagement | VPSA/VPAA | 2024-2027 | VPSA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Establish an office of applied learning and community engagement to develop, coordinate, and promote internships, co-ops, service-learning, and undergraduate research in collaboration with academic departments, community partners, and employers. (1,2,5) | Establish an office of applied learning and community engagement | VPSA/VPAA | 2024-2027 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Establish an office of applied learning and community engagement to develop, coordinate, and promote internships, co-ops, service-learning, and undergraduate research in collaboration with academic departments, community partners, and employers. (1,2,5) | Establish an office of applied learning and community engagement | VPSA/VPAA | 2024-2027 | VPSA
SSE Outcome 5: Incorporate in experiential learning opportunities (including practicum, internships, research projects, community engagement) in undergraduate degree curriculum, by cataloging current opportunities by the end of 2024-25 with 100% of programs reaching experiential learning integration by 2028-29. | Establish an office of applied learning and community engagement to develop, coordinate, and promote internships, co-ops, service-learning, and undergraduate research in collaboration with academic departments, community partners, and employers. (1,2,5) | Establish an office of applied learning and community engagement | VPSA/VPAA | 2024-2027 | VPAA
SSE Outcome 5: Incorporate in experiential learning opportunities (including practicum, internships, research projects, community engagement) in undergraduate degree curriculum, by cataloging current opportunities by the end of 2024-25 with 100% of programs reaching experiential learning integration by 2028-29. | Establish an office of applied learning and community engagement to develop, coordinate, and promote internships, co-ops, service-learning, and undergraduate research in collaboration with academic departments, community partners, and employers. (1,2,5) | Establish an office of applied learning and community engagement | VPSA/VPAA | 2024-2027 | VPSA
RA/RI Outcome 4: By 2026-2027, 25% of the faculty will participate in community engagement activities, increasing to 75% by 2028-2029. | Establish and/or strengthen programs and commitment to community engagement (e.g., applied learning, alumni and philanthropic engagement, etc.) (4,6,7) | Establish and/or strengthen programs and commitment to community engagement | VPAA/VPSA | 2024-2027 | VPAA
RA/RI Outcome 4: By 2026-2027, 25% of the faculty will participate in community engagement activities, increasing to 75% by 2028-2029. | Establish and/or strengthen programs and commitment to community engagement (e.g., applied learning, alumni and philanthropic engagement, etc.) (4,6,7) | Establish and/or strengthen programs and commitment to community engagement | VPAA/VPSA | 2024-2027 | VPSA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | Establish and/or strengthen programs and commitment to community engagement (e.g., applied learning, alumni and philanthropic engagement, etc.) (4,6,7) | Establish and/or strengthen programs and commitment to community engagement | VPAA/VPSA | 2024-2027 | VPAA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | Establish and/or strengthen programs and commitment to community engagement (e.g., applied learning, alumni and philanthropic engagement, etc.) (4,6,7) | Establish and/or strengthen programs and commitment to community engagement | VPAA/VPSA | 2024-2027 | VPSA
RA/RI Outcome 7: By 2028-2029, EWU will develop a multi-year investment and change-management plan that coordinates major state and institutional infrastructure investments with the development of faculty, student, and community engagement programs. | Establish and/or strengthen programs and commitment to community engagement (e.g., applied learning, alumni and philanthropic engagement, etc.) (4,6,7) | Establish and/or strengthen programs and commitment to community engagement | VPAA/VPSA | 2024-2027 | VPAA
RA/RI Outcome 7: By 2028-2029, EWU will develop a multi-year investment and change-management plan that coordinates major state and institutional infrastructure investments with the development of faculty, student, and community engagement programs. | Establish and/or strengthen programs and commitment to community engagement (e.g., applied learning, alumni and philanthropic engagement, etc.) (4,6,7) | Establish and/or strengthen programs and commitment to community engagement | VPAA/VPSA | 2024-2027 | VPSA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Leverage the comprehensive campaign to expand scholarship opportunities and support student financial needs. (1,2) | Expand scholarship opportunities | VPUA | 2025-2027 | VPUA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Leverage the comprehensive campaign to expand scholarship opportunities and support student financial needs. (1,2) | Expand scholarship opportunities | VPUA | 2025-2027 | VPUA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPBS
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPBS
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPAA
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPBS
SSE Outcome 4: By 2028-2029, decrease the DFW (Drop, Fail, and Withdrawal) rates in courses with historically high DFW rates and reduce the DFW rates for all courses to less than 20%. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPAA
SSE Outcome 4: By 2028-2029, decrease the DFW (Drop, Fail, and Withdrawal) rates in courses with historically high DFW rates and reduce the DFW rates for all courses to less than 20%. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPBS
IIPP Outcome 3: By 2025-2026, EWU will develop a campus master plan, which will explicitly incorporate residence halls, and include a vision for both Cheney and Spokane locations. | EWU will identify a vision for all campuses (SIERR, Catalyst, Health Science/WSU), have targeted events, and integrate the Campuses into Cheney where appropriate. (3) | Identify a vision for all academic centers | VPAA/President's Office | 2024-2027 | President's Office
IIPP Outcome 3: By 2025-2026, EWU will develop a campus master plan, which will explicitly incorporate residence halls, and include a vision for both Cheney and Spokane locations. | EWU will identify a vision for all campuses (SIERR, Catalyst, Health Science/WSU), have targeted events, and integrate the Campuses into Cheney where appropriate. (3) | Identify a vision for all academic centers | VPAA/President's Office | 2024-2027 | VPAA
Belonging Outcome 3: By 2026-2027, the number of students who participate in a university mentoring program or university support service will increase by 10% and participants will have a 10% greater outcome (measured by retention and graduation) than those who did not participate in a mentorship opportunity. | Implement online synchronous and asynchronous, as well as in-person opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning, while educating participants about co-curricular offerings available to students. (3,4) | Implement opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning | VPAA/VPPC/President's Office | 2024-2029 | President's Office
Belonging Outcome 3: By 2026-2027, the number of students who participate in a university mentoring program or university support service will increase by 10% and participants will have a 10% greater outcome (measured by retention and graduation) than those who did not participate in a mentorship opportunity. | Implement online synchronous and asynchronous, as well as in-person opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning, while educating participants about co-curricular offerings available to students. (3,4) | Implement opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning | VPAA/VPPC/President's Office | 2024-2029 | VPAA
Belonging Outcome 3: By 2026-2027, the number of students who participate in a university mentoring program or university support service will increase by 10% and participants will have a 10% greater outcome (measured by retention and graduation) than those who did not participate in a mentorship opportunity. | Implement online synchronous and asynchronous, as well as in-person opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning, while educating participants about co-curricular offerings available to students. (3,4) | Implement opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning | VPAA/VPPC/President's Office | 2024-2029 | VPPC
Belonging Outcome 4: By 2027-2028, 100% of faculty and staff will have participated in formal training opportunities to support their growth in culturally responsive teaching and learning support, emphasizing curricular and co-curricular learning spaces (e.g., Inclusive Teaching Academy). | Implement online synchronous and asynchronous, as well as in-person opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning, while educating participants about co-curricular offerings available to students. (3,4) | Implement opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning | VPAA/VPPC/President's Office | 2024-2029 | President's Office
Belonging Outcome 4: By 2027-2028, 100% of faculty and staff will have participated in formal training opportunities to support their growth in culturally responsive teaching and learning support, emphasizing curricular and co-curricular learning spaces (e.g., Inclusive Teaching Academy). | Implement online synchronous and asynchronous, as well as in-person opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning, while educating participants about co-curricular offerings available to students. (3,4) | Implement opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning | VPAA/VPPC/President's Office | 2024-2029 | VPAA
Belonging Outcome 4: By 2027-2028, 100% of faculty and staff will have participated in formal training opportunities to support their growth in culturally responsive teaching and learning support, emphasizing curricular and co-curricular learning spaces (e.g., Inclusive Teaching Academy). | Implement online synchronous and asynchronous, as well as in-person opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning, while educating participants about co-curricular offerings available to students. (3,4) | Implement opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning | VPAA/VPPC/President's Office | 2024-2029 | VPPC
IIPP Outcome 2: Increase the recruitment of qualified applicants for all permanent EWU positions by 1% annually, and align employee demographics with the diversity of the EWU student population. | Implement targeted recruitment initiatives that actively seek out qualified applicants from diverse backgrounds, and collaborate with diverse professional organizations to widen the pool of potential candidates. (2) | Implement targeted recruitment initiatives | VPPC | 2024-2029 | VPPC
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Implement targeted support programs and initiatives focused on academic, financial, and social resources specifically designed to address the unique challenges faced by historically marginalized student populations. (1,2) | Implement targeted support programs with a focus on historically marginalized populations | VPAA/VPSA | 2024-2026 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Implement targeted support programs and initiatives focused on academic, financial, and social resources specifically designed to address the unique challenges faced by historically marginalized student populations. (1,2) | Implement targeted support programs with a focus on historically marginalized populations | VPAA/VPSA | 2024-2026 | VPSA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Implement targeted support programs and initiatives focused on academic, financial, and social resources specifically designed to address the unique challenges faced by historically marginalized student populations. (1,2) | Implement targeted support programs with a focus on historically marginalized populations | VPAA/VPSA | 2024-2026 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Implement targeted support programs and initiatives focused on academic, financial, and social resources specifically designed to address the unique challenges faced by historically marginalized student populations. (1,2) | Implement targeted support programs with a focus on historically marginalized populations | VPAA/VPSA | 2024-2026 | VPSA
RA/RI Outcome 3: By 2025-2026, EWU will complete a comprehensive regional economic profile using data-driven analytics and use that profile to promote academic offerings that benefit our region in preparation for the development of an academic master plan. | EWU will invest in programmatic offerings that align with regional economic activities. (3,6) | Invest in programmatic offerings that align with regional economic activities | VPAA | 2025-2029 | VPAA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | EWU will invest in programmatic offerings that align with regional economic activities. (3,6) | Invest in programmatic offerings that align with regional economic activities | VPAA | 2025-2029 | VPAA
Belonging Outcome 6: Beginning in 2024, increase alumni engagement by 20% each year through various means of time (e.g., volunteerism on boards, etc.), talent (e.g., utilizing their profession), and treasures (e.g., giving), further, investing in an active alumni culture. | Utilizing private funds raised through a comprehensive campaign to name centers, schools, and programs, and identifying corporate partners or philanthropic gift(s) to name our stadium and gymnasium (6). | Name centers, schools, and programs, and identifying corporate partners or philanthropic gift(s) to name our stadium and gymnasium | VPUA/DOA | 2026-2029 | DOA
Belonging Outcome 6: Beginning in 2024, increase alumni engagement by 20% each year through various means of time (e.g., volunteerism on boards, etc.), talent (e.g., utilizing their profession), and treasures (e.g., giving), further, investing in an active alumni culture. | Utilizing private funds raised through a comprehensive campaign to name centers, schools, and programs, and identifying corporate partners or philanthropic gift(s) to name our stadium and gymnasium (6). | Name centers, schools, and programs, and identifying corporate partners or philanthropic gift(s) to name our stadium and gymnasium | VPUA/DOA | 2026-2029 | VPUA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Revamp First Year Experience, starting with strong pre-student programming, including New Student Orientation and Summer Bridge Programs. (1,2) | Revamp First Year Experience Programming | VPAA/VPSA | 2024-2026 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Revamp First Year Experience, starting with strong pre-student programming, including New Student Orientation and Summer Bridge Programs. (1,2) | Revamp First Year Experience Programming | VPAA/VPSA | 2024-2026 | VPSA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Revamp First Year Experience, starting with strong pre-student programming, including New Student Orientation and Summer Bridge Programs. (1,2) | Revamp First Year Experience Programming | VPAA/VPSA | 2024-2026 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Revamp First Year Experience, starting with strong pre-student programming, including New Student Orientation and Summer Bridge Programs. (1,2) | Revamp First Year Experience Programming | VPAA/VPSA | 2024-2026 | VPSA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Review and optimize course scheduling practices to better accommodate student needs and preferences. (1,2,3,4) | Review and optimize course scheduling | VPAA | 2025-2027 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Review and optimize course scheduling practices to better accommodate student needs and preferences. (1,2,3,4) | Review and optimize course scheduling | VPAA | 2025-2027 | VPAA
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Review and optimize course scheduling practices to better accommodate student needs and preferences. (1,2,3,4) | Review and optimize course scheduling | VPAA | 2025-2027 | VPAA
SSE Outcome 4: By 2028-2029, decrease the DFW (Drop, Fail, and Withdrawal) rates in courses with historically high DFW rates and reduce the DFW rates for all courses to less than 20%. | Review and optimize course scheduling practices to better accommodate student needs and preferences. (1,2,3,4) | Review and optimize course scheduling | VPAA | 2025-2027 | VPAA
Belonging Outcome 1: By 2025-2026, all university and academic policies, including those specific to individual units, will undergo an equity-minded audit to identify policies and practices contributing to inequitable outcomes for historically underrepresented students/faculty/staff. | Select a self-auditing process and offer training to unit-level participants. The audit process will be developed, trained, and monitored. (1,2) | Select a self-auditing process | VPPC | 2025-2028 | VPPC
Belonging Outcome 2: By 2027-2028, all academic and student support units will implement equity-minded accountability and assessment practices and an annual reporting instrument that includes measures such as the participation and/or success rates of students disaggregated by race/ethnicity, socioeconomic status, and gender. | Select a self-auditing process and offer training to unit-level participants. The audit process will be developed, trained, and monitored. (1,2) | Select a self-auditing process | VPPC | 2025-2028 | VPPC
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Simplify degree pathways to ensure clarity and ease of progression toward graduation, including identifying and eliminating bottleneck courses that hinder student progress and timely graduation. (1,2,3,4) | Simplify degree pathways | VPAA | 2025-2027 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Simplify degree pathways to ensure clarity and ease of progression toward graduation, including identifying and eliminating bottleneck courses that hinder student progress and timely graduation. (1,2,3,4) | Simplify degree pathways | VPAA | 2025-2027 | VPAA
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Simplify degree pathways to ensure clarity and ease of progression toward graduation, including identifying and eliminating bottleneck courses that hinder student progress and timely graduation. (1,2,3,4) | Simplify degree pathways | VPAA | 2025-2027 | VPAA
SSE Outcome 4: By 2028-2029, decrease the DFW (Drop, Fail, and Withdrawal) rates in courses with historically high DFW rates and reduce the DFW rates for all courses to less than 20%. | Simplify degree pathways to ensure clarity and ease of progression toward graduation, including identifying and eliminating bottleneck courses that hinder student progress and timely graduation. (1,2,3,4) | Simplify degree pathways | VPAA | 2025-2027 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Strengthen cross-divisional collaborative partnerships to provide students with holistic and supportive experiences. (1,2,3) | Strengthen cross-divisional collaborative partnership | ELT | 2024-2027 | ELT
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Strengthen cross-divisional collaborative partnerships to provide students with holistic and supportive experiences. (1,2,3) | Strengthen cross-divisional collaborative partnership | ELT | 2024-2027 | ELT
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Strengthen cross-divisional collaborative partnerships to provide students with holistic and supportive experiences. (1,2,3) | Strengthen cross-divisional collaborative partnership | ELT | 2024-2027 | ELT
IIPP Outcome 3: By 2025-2026, EWU will develop a campus master plan, which will explicitly incorporate residence halls, and include a vision for both Cheney and Spokane locations. | Our facilities and technology will support excellence in education and provide an intentional and predictable roadmap for development, remain flexible to respond to educational demands, strengthen our IT infrastructure, and become a model for other institutions. Incorporate campaign funds to enhance campus facilities and technological infrastructure, supporting excellence in education and fostering community integration. (3) | Support excellence in education by strengthening infrastructure | VPBS | 2024-2027 | VPBS
Belonging Outcome 2: By 2027-2028, all academic and student support units will implement equity-minded accountability and assessment practices and an annual reporting instrument that includes measures such as the participation and/or success rates of students disaggregated by race/ethnicity, socioeconomic status, and gender. | Develop an annual reporting instrument to track DEI progress closing equity gaps by each division and college. (2) | Track DEI progress closing equity gaps by each division and college | VPAA | 2026-2028 | VPAA
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | EWU will analyze faculty and staff turnover to develop, implement, and evaluate programs to improve recruitment and increase retention. (1,2) | Analyze faculty and staff turnover | VPBS/VPPC | 2025-2027 | VPPC
IIPP Outcome 2: Increase the recruitment of qualified applicants for all permanent EWU positions by 1% annually, and align employee demographics with the diversity of the EWU student population. | EWU will analyze faculty and staff turnover to develop, implement, and evaluate programs to improve recruitment and increase retention. (1,2) | Analyze faculty and staff turnover | VPBS/VPPC | 2025-2027 | VPPC

## President's Office
University Outcomes (Performance Target/Metric) | Activity | Activity *Short* Name | RESPONSIBILITY | TIMELINE | RESPONSIBLE_PARTY
Belonging Outcome 2: By 2027-2028, all academic and student support units will implement equity-minded accountability and assessment practices and an annual reporting instrument that includes measures such as the participation and/or success rates of students disaggregated by race/ethnicity, socioeconomic status, and gender. | Create a directory of DEI experts across campus and a repository of DEI resources. (2,5) | Create a directory of DEI experts across campus | President's Office | 2024-2025 | President's Office
Belonging Outcome 5: By 2027-2028, all of EWU will have an improved sense of belonging by improved student journey mapping, onboarding, and training experiences to include surveys of satisfaction and exit interview feedback to increase sense of belonging for all. | Create a directory of DEI experts across campus and a repository of DEI resources. (2,5) | Create a directory of DEI experts across campus | President's Office | 2024-2025 | President's Office
Belonging Outcome 5: By 2027-2028, all of EWU will have an improved sense of belonging by improved student journey mapping, onboarding, and training experiences to include surveys of satisfaction and exit interview feedback to increase sense of belonging for all. | Develop resources for university employees for successful onboarding and integration into university and community. (5) | Develop resources for successful onboarding | VPPC/President's Office | 2024-2025 | President's Office
IIPP Outcome 3: By 2025-2026, EWU will develop a campus master plan, which will explicitly incorporate residence halls, and include a vision for both Cheney and Spokane locations. | EWU will identify a vision for all campuses (SIERR, Catalyst, Health Science/WSU), have targeted events, and integrate the Campuses into Cheney where appropriate. (3) | Identify a vision for all academic centers | VPAA/President's Office | 2024-2027 | President's Office
Belonging Outcome 3: By 2026-2027, the number of students who participate in a university mentoring program or university support service will increase by 10% and participants will have a 10% greater outcome (measured by retention and graduation) than those who did not participate in a mentorship opportunity. | Implement online synchronous and asynchronous, as well as in-person opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning, while educating participants about co-curricular offerings available to students. (3,4) | Implement opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning | VPAA/VPPC/President's Office | 2024-2029 | President's Office
Belonging Outcome 4: By 2027-2028, 100% of faculty and staff will have participated in formal training opportunities to support their growth in culturally responsive teaching and learning support, emphasizing curricular and co-curricular learning spaces (e.g., Inclusive Teaching Academy). | Implement online synchronous and asynchronous, as well as in-person opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning, while educating participants about co-curricular offerings available to students. (3,4) | Implement opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning | VPAA/VPPC/President's Office | 2024-2029 | President's Office

## ELT
University Outcomes (Performance Target/Metric) | Activity | Activity *Short* Name | RESPONSIBILITY | TIMELINE | RESPONSIBLE_PARTY
Belonging Outcome 1: By 2025-2026, all university and academic policies, including those specific to individual units, will undergo an equity-minded audit to identify policies and practices contributing to inequitable outcomes for historically underrepresented students/faculty/staff. | Based on the audit findings, develop and implement comprehensive action plans to revise policies, promote inclusivity, and ensure equitable opportunities and outcomes for all students, faculty, and staff. (1,2) | Based on the audit findings, develop and implement comprehensive action plans | VPPC/ELT | 2026-2029 | ELT
Belonging Outcome 2: By 2027-2028, all academic and student support units will implement equity-minded accountability and assessment practices and an annual reporting instrument that includes measures such as the participation and/or success rates of students disaggregated by race/ethnicity, socioeconomic status, and gender. | Based on the audit findings, develop and implement comprehensive action plans to revise policies, promote inclusivity, and ensure equitable opportunities and outcomes for all students, faculty, and staff. (1,2) | Based on the audit findings, develop and implement comprehensive action plans | VPPC/ELT | 2026-2029 | ELT
Belonging Outcome 5: By 2027-2028, all of EWU will have an improved sense of belonging by improved student journey mapping, onboarding, and training experiences to include surveys of satisfaction and exit interview feedback to increase sense of belonging for all. | Create detailed student journey maps from admission to graduation using satisfaction surveys and using feedback to continuously refine policies and practices to foster a more inclusive and supportive environment. (5) | Create detailed student journey maps from admission to graduation | ELT | 2024-2029 | ELT
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Strengthen cross-divisional collaborative partnerships to provide students with holistic and supportive experiences. (1,2,3) | Strengthen cross-divisional collaborative partnership | ELT | 2024-2027 | ELT
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Strengthen cross-divisional collaborative partnerships to provide students with holistic and supportive experiences. (1,2,3) | Strengthen cross-divisional collaborative partnership | ELT | 2024-2027 | ELT
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Strengthen cross-divisional collaborative partnerships to provide students with holistic and supportive experiences. (1,2,3) | Strengthen cross-divisional collaborative partnership | ELT | 2024-2027 | ELT

## Athletics
University Outcomes (Performance Target/Metric) | Activity | Activity *Short* Name | RESPONSIBILITY | TIMELINE | RESPONSIBLE_PARTY
Belonging Outcome 6: Beginning in 2024, increase alumni engagement by 20% each year through various means of time (e.g., volunteerism on boards, etc.), talent (e.g., utilizing their profession), and treasures (e.g., giving), further, investing in an active alumni culture. | Expand alumni engagement through athletic and community events (on campus and off campus), career development, mentorship programs, volunteer opportunities, fundraising campaigns, professional expertise programs, regular events, and a recognition program to foster a vibrant alumni community. (6) | Expand alumni engagement through athletic and community events | VPUA/DOA | 2024-2027 | DOA
RA/RI Outcome 2:By 2025-2026, EWU will develop a comprehensive brand and identity marketing plan that supports the future of the university. | Enhance EWU's brand recognition and reputation by creating a unified and compelling brand message that resonates with prospective students, alumni, and the community. (2) | Create a unified and compelling brand message | VPUA/DOA | 2024-2028 | DOA
Belonging Outcome 6: Beginning in 2024, increase alumni engagement by 20% each year through various means of time (e.g., volunteerism on boards, etc.), talent (e.g., utilizing their profession), and treasures (e.g., giving), further, investing in an active alumni culture. | Utilizing private funds raised through a comprehensive campaign to name centers, schools, and programs, and identifying corporate partners or philanthropic gift(s) to name our stadium and gymnasium (6). | Name centers, schools, and programs, and identifying corporate partners or philanthropic gift(s) to name our stadium and gymnasium | VPUA/DOA | 2026-2029 | DOA

## Academic Affairs
University Outcomes (Performance Target/Metric) | Activity | Activity *Short* Name | RESPONSIBILITY | TIMELINE | RESPONSIBLE_PARTY
RA/RI Outcome 1: By the end of 2024-2025, EWU will finalize its decarbonization plan which will describe how the University will eliminate its greenhouse gas emissions and improve the University’s climate resilience. By the end of 2025-2026 the plan will be updated to describe how students, faculty and staff will be involved in plan development and implementation | Establish a cross-functional sustainability task force to develop and finalize a decarbonization plan that ensures involvement of students, faculty, and staff. (1) | Establish a cross-functional sustainability task force | VPBS / VPAA | 2024-2029 | VPAA
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | Offer staff in service programs and an annual faculty retreat (1,5) | Offer staff in service programs and an annual faculty retreat | VPPC/VPAA | 2024-2029 | VPAA
IIPP Outcome 5: By 2026-2027, 100% of staff will participate in a professional development opportunity annually | Offer staff in service programs and an annual faculty retreat (1,5) | Offer staff in service programs and an annual faculty retreat | VPPC/VPAA | 2024-2029 | VPAA
RA/RI Outcome 3: By 2025-2026, EWU will complete a comprehensive regional economic profile using data-driven analytics and use that profile to promote academic offerings that benefit our region in preparation for the development of an academic master plan. | EWU will align its programmatic offerings with regional economic activities by identifying top in-demand jobs and their required skills, creating a catalog of these skills, and then updating existing programs or developing new ones to incorporate these skill sets. (3,4,6,7) | Align programmatic offerings with regional economic activities | VPAA | 2025-2029 | VPAA
RA/RI Outcome 4: By 2026-2027, 25% of the faculty will participate in community engagement activities, increasing to 75% by 2028-2029. | EWU will align its programmatic offerings with regional economic activities by identifying top in-demand jobs and their required skills, creating a catalog of these skills, and then updating existing programs or developing new ones to incorporate these skill sets. (3,4,6,7) | Align programmatic offerings with regional economic activities | VPAA | 2025-2029 | VPAA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | EWU will align its programmatic offerings with regional economic activities by identifying top in-demand jobs and their required skills, creating a catalog of these skills, and then updating existing programs or developing new ones to incorporate these skill sets. (3,4,6,7) | Align programmatic offerings with regional economic activities | VPAA | 2025-2029 | VPAA
RA/RI Outcome 7: By 2028-2029, EWU will develop a multi-year investment and change-management plan that coordinates major state and institutional infrastructure investments with the development of faculty, student, and community engagement programs. | EWU will align its programmatic offerings with regional economic activities by identifying top in-demand jobs and their required skills, creating a catalog of these skills, and then updating existing programs or developing new ones to incorporate these skill sets. (3,4,6,7) | Align programmatic offerings with regional economic activities | VPAA | 2025-2029 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Conduct a detailed analysis of the past five years to identify courses with high DFW rates and develop effective interventions and ongoing assessment of these courses. (1,2,4) | Analyze high DFW rate courses | VPAA | 2024-2029 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Conduct a detailed analysis of the past five years to identify courses with high DFW rates and develop effective interventions and ongoing assessment of these courses. (1,2,4) | Analyze high DFW rate courses | VPAA | 2024-2029 | VPAA
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Conduct a detailed analysis of the past five years to identify courses with high DFW rates and develop effective interventions and ongoing assessment of these courses. (1,2,4) | Analyze high DFW rate courses | VPAA | 2024-2029 | VPAA
Belonging Outcome 3: By 2026-2027, the number of students who participate in a university mentoring program or university support service will increase by 10% and participants will have a 10% greater outcome (measured by retention and graduation) than those who did not participate in a mentorship opportunity. | By the end of the 2027 academic year, EWU will establish a framework to effectively communicate, coordinate, support, track, and assess mentorship and university support service opportunities (3) | Assess mentorship and university support service opportunities | VPAA/VPSA | 2026-2028 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Conduct an inventory and needs assessment to enhance academic support services and develop opportunities, such as Supplemental Instruction, across the university. (1,2,3,4) | Conduct a needs assessment for student support services | VPAA | 2024-2026 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Conduct an inventory and needs assessment to enhance academic support services and develop opportunities, such as Supplemental Instruction, across the university. (1,2,3,4) | Conduct a needs assessment for student support services | VPAA | 2024-2026 | VPAA
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Conduct an inventory and needs assessment to enhance academic support services and develop opportunities, such as Supplemental Instruction, across the university. (1,2,3,4) | Conduct a needs assessment for student support services | VPAA | 2024-2026 | VPAA
SSE Outcome 4: By 2028-2029, decrease the DFW (Drop, Fail, and Withdrawal) rates in courses with historically high DFW rates and reduce the DFW rates for all courses to less than 20%. | Conduct an inventory and needs assessment to enhance academic support services and develop opportunities, such as Supplemental Instruction, across the university. (1,2,3,4) | Conduct a needs assessment for student support services | VPAA | 2024-2026 | VPAA
RA/RI Outcome 3: By 2025-2026, EWU will complete a comprehensive regional economic profile using data-driven analytics and use that profile to promote academic offerings that benefit our region in preparation for the development of an academic master plan. | EWU will develop a joint urban planning framework with Cheney and the West Plains to align campus development with regional growth, fostering professional partnerships and student opportunities. (3,6) | Develop a joint urban planning framework with Cheney and the West Plain | VPAA / VPBS / VPSA | 2025-2027 | VPAA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | EWU will develop a joint urban planning framework with Cheney and the West Plains to align campus development with regional growth, fostering professional partnerships and student opportunities. (3,6) | Develop a joint urban planning framework with Cheney and the West Plain | VPAA / VPBS / VPSA | 2025-2027 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Develop and implement the strategic enrollment management plan. (1,2) | Develop strategic enrollment management plan | VPAA | 2024-2028 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Develop and implement the strategic enrollment management plan. (1,2) | Develop strategic enrollment management plan | VPAA | 2024-2028 | VPAA
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | Enhance faculty and staff well-being and resilience with a data-informed approach (1,4) | Enhance faculty and staff well-being | VPBS/VPAA | 2025-2027 | VPAA
IIPP Outcome 4: Overall campus Climate Survey score will increase by 10% in 2027-2028 and meet or exceed other peer and national institutions. | Enhance faculty and staff well-being and resilience with a data-informed approach (1,4) | Enhance faculty and staff well-being | VPBS/VPAA | 2025-2027 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Establish an office of applied learning and community engagement to develop, coordinate, and promote internships, co-ops, service-learning, and undergraduate research in collaboration with academic departments, community partners, and employers. (1,2,5) | Establish an office of applied learning and community engagement | VPSA/VPAA | 2024-2027 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Establish an office of applied learning and community engagement to develop, coordinate, and promote internships, co-ops, service-learning, and undergraduate research in collaboration with academic departments, community partners, and employers. (1,2,5) | Establish an office of applied learning and community engagement | VPSA/VPAA | 2024-2027 | VPAA
SSE Outcome 5: Incorporate in experiential learning opportunities (including practicum, internships, research projects, community engagement) in undergraduate degree curriculum, by cataloging current opportunities by the end of 2024-25 with 100% of programs reaching experiential learning integration by 2028-29. | Establish an office of applied learning and community engagement to develop, coordinate, and promote internships, co-ops, service-learning, and undergraduate research in collaboration with academic departments, community partners, and employers. (1,2,5) | Establish an office of applied learning and community engagement | VPSA/VPAA | 2024-2027 | VPAA
RA/RI Outcome 4: By 2026-2027, 25% of the faculty will participate in community engagement activities, increasing to 75% by 2028-2029. | Establish and/or strengthen programs and commitment to community engagement (e.g., applied learning, alumni and philanthropic engagement, etc.) (4,6,7) | Establish and/or strengthen programs and commitment to community engagement | VPAA/VPSA | 2024-2027 | VPAA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | Establish and/or strengthen programs and commitment to community engagement (e.g., applied learning, alumni and philanthropic engagement, etc.) (4,6,7) | Establish and/or strengthen programs and commitment to community engagement | VPAA/VPSA | 2024-2027 | VPAA
RA/RI Outcome 7: By 2028-2029, EWU will develop a multi-year investment and change-management plan that coordinates major state and institutional infrastructure investments with the development of faculty, student, and community engagement programs. | Establish and/or strengthen programs and commitment to community engagement (e.g., applied learning, alumni and philanthropic engagement, etc.) (4,6,7) | Establish and/or strengthen programs and commitment to community engagement | VPAA/VPSA | 2024-2027 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPAA
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPAA
SSE Outcome 4: By 2028-2029, decrease the DFW (Drop, Fail, and Withdrawal) rates in courses with historically high DFW rates and reduce the DFW rates for all courses to less than 20%. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPAA
IIPP Outcome 3: By 2025-2026, EWU will develop a campus master plan, which will explicitly incorporate residence halls, and include a vision for both Cheney and Spokane locations. | EWU will identify a vision for all campuses (SIERR, Catalyst, Health Science/WSU), have targeted events, and integrate the Campuses into Cheney where appropriate. (3) | Identify a vision for all academic centers | VPAA/President's Office | 2024-2027 | VPAA
Belonging Outcome 3: By 2026-2027, the number of students who participate in a university mentoring program or university support service will increase by 10% and participants will have a 10% greater outcome (measured by retention and graduation) than those who did not participate in a mentorship opportunity. | Implement online synchronous and asynchronous, as well as in-person opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning, while educating participants about co-curricular offerings available to students. (3,4) | Implement opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning | VPAA/VPPC/President's Office | 2024-2029 | VPAA
Belonging Outcome 4: By 2027-2028, 100% of faculty and staff will have participated in formal training opportunities to support their growth in culturally responsive teaching and learning support, emphasizing curricular and co-curricular learning spaces (e.g., Inclusive Teaching Academy). | Implement online synchronous and asynchronous, as well as in-person opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning, while educating participants about co-curricular offerings available to students. (3,4) | Implement opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning | VPAA/VPPC/President's Office | 2024-2029 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Implement targeted support programs and initiatives focused on academic, financial, and social resources specifically designed to address the unique challenges faced by historically marginalized student populations. (1,2) | Implement targeted support programs with a focus on historically marginalized populations | VPAA/VPSA | 2024-2026 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Implement targeted support programs and initiatives focused on academic, financial, and social resources specifically designed to address the unique challenges faced by historically marginalized student populations. (1,2) | Implement targeted support programs with a focus on historically marginalized populations | VPAA/VPSA | 2024-2026 | VPAA
RA/RI Outcome 3: By 2025-2026, EWU will complete a comprehensive regional economic profile using data-driven analytics and use that profile to promote academic offerings that benefit our region in preparation for the development of an academic master plan. | EWU will invest in programmatic offerings that align with regional economic activities. (3,6) | Invest in programmatic offerings that align with regional economic activities | VPAA | 2025-2029 | VPAA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | EWU will invest in programmatic offerings that align with regional economic activities. (3,6) | Invest in programmatic offerings that align with regional economic activities | VPAA | 2025-2029 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Revamp First Year Experience, starting with strong pre-student programming, including New Student Orientation and Summer Bridge Programs. (1,2) | Revamp First Year Experience Programming | VPAA/VPSA | 2024-2026 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Revamp First Year Experience, starting with strong pre-student programming, including New Student Orientation and Summer Bridge Programs. (1,2) | Revamp First Year Experience Programming | VPAA/VPSA | 2024-2026 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Review and optimize course scheduling practices to better accommodate student needs and preferences. (1,2,3,4) | Review and optimize course scheduling | VPAA | 2025-2027 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Review and optimize course scheduling practices to better accommodate student needs and preferences. (1,2,3,4) | Review and optimize course scheduling | VPAA | 2025-2027 | VPAA
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Review and optimize course scheduling practices to better accommodate student needs and preferences. (1,2,3,4) | Review and optimize course scheduling | VPAA | 2025-2027 | VPAA
SSE Outcome 4: By 2028-2029, decrease the DFW (Drop, Fail, and Withdrawal) rates in courses with historically high DFW rates and reduce the DFW rates for all courses to less than 20%. | Review and optimize course scheduling practices to better accommodate student needs and preferences. (1,2,3,4) | Review and optimize course scheduling | VPAA | 2025-2027 | VPAA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Simplify degree pathways to ensure clarity and ease of progression toward graduation, including identifying and eliminating bottleneck courses that hinder student progress and timely graduation. (1,2,3,4) | Simplify degree pathways | VPAA | 2025-2027 | VPAA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Simplify degree pathways to ensure clarity and ease of progression toward graduation, including identifying and eliminating bottleneck courses that hinder student progress and timely graduation. (1,2,3,4) | Simplify degree pathways | VPAA | 2025-2027 | VPAA
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Simplify degree pathways to ensure clarity and ease of progression toward graduation, including identifying and eliminating bottleneck courses that hinder student progress and timely graduation. (1,2,3,4) | Simplify degree pathways | VPAA | 2025-2027 | VPAA
SSE Outcome 4: By 2028-2029, decrease the DFW (Drop, Fail, and Withdrawal) rates in courses with historically high DFW rates and reduce the DFW rates for all courses to less than 20%. | Simplify degree pathways to ensure clarity and ease of progression toward graduation, including identifying and eliminating bottleneck courses that hinder student progress and timely graduation. (1,2,3,4) | Simplify degree pathways | VPAA | 2025-2027 | VPAA
Belonging Outcome 2: By 2027-2028, all academic and student support units will implement equity-minded accountability and assessment practices and an annual reporting instrument that includes measures such as the participation and/or success rates of students disaggregated by race/ethnicity, socioeconomic status, and gender. | Develop an annual reporting instrument to track DEI progress closing equity gaps by each division and college. (2) | Track DEI progress closing equity gaps by each division and college | VPAA | 2026-2028 | VPAA

## University Advancement
University Outcomes (Performance Target/Metric) | Activity | Activity *Short* Name | RESPONSIBILITY | TIMELINE | RESPONSIBLE_PARTY
Belonging Outcome 6: Beginning in 2024, increase alumni engagement by 20% each year through various means of time (e.g., volunteerism on boards, etc.), talent (e.g., utilizing their profession), and treasures (e.g., giving), further, investing in an active alumni culture. | Expand alumni engagement through athletic and community events (on campus and off campus), career development, mentorship programs, volunteer opportunities, fundraising campaigns, professional expertise programs, regular events, and a recognition program to foster a vibrant alumni community. (6) | Expand alumni engagement through athletic and community events | VPUA/DOA | 2024-2027 | VPUA
RA/RI Outcome 2:By 2025-2026, EWU will develop a comprehensive brand and identity marketing plan that supports the future of the university. | Enhance EWU's brand recognition and reputation by creating a unified and compelling brand message that resonates with prospective students, alumni, and the community. (2) | Create a unified and compelling brand message | VPUA/DOA | 2024-2028 | VPUA
RA/RI Outcome 4: By 2026-2027, 25% of the faculty will participate in community engagement activities, increasing to 75% by 2028-2029. | Enhance applied learning opportunities with specific fundraising for these student opportunities. (4,6,7) | Enhance applied learning opportunities | VPSA/VPUA | 2024-2027 | VPUA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | Enhance applied learning opportunities with specific fundraising for these student opportunities. (4,6,7) | Enhance applied learning opportunities | VPSA/VPUA | 2024-2027 | VPUA
RA/RI Outcome 7: By 2028-2029, EWU will develop a multi-year investment and change-management plan that coordinates major state and institutional infrastructure investments with the development of faculty, student, and community engagement programs. | Enhance applied learning opportunities with specific fundraising for these student opportunities. (4,6,7) | Enhance applied learning opportunities | VPSA/VPUA | 2024-2027 | VPUA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Leverage the comprehensive campaign to expand scholarship opportunities and support student financial needs. (1,2) | Expand scholarship opportunities | VPUA | 2025-2027 | VPUA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Leverage the comprehensive campaign to expand scholarship opportunities and support student financial needs. (1,2) | Expand scholarship opportunities | VPUA | 2025-2027 | VPUA
Belonging Outcome 6: Beginning in 2024, increase alumni engagement by 20% each year through various means of time (e.g., volunteerism on boards, etc.), talent (e.g., utilizing their profession), and treasures (e.g., giving), further, investing in an active alumni culture. | Utilizing private funds raised through a comprehensive campaign to name centers, schools, and programs, and identifying corporate partners or philanthropic gift(s) to name our stadium and gymnasium (6). | Name centers, schools, and programs, and identifying corporate partners or philanthropic gift(s) to name our stadium and gymnasium | VPUA/DOA | 2026-2029 | VPUA

## Business and Strategy
University Outcomes (Performance Target/Metric) | Activity | Activity *Short* Name | RESPONSIBILITY | TIMELINE | RESPONSIBLE_PARTY
RA/RI Outcome 1: By the end of 2024-2025, EWU will finalize its decarbonization plan which will describe how the University will eliminate its greenhouse gas emissions and improve the University’s climate resilience. By the end of 2025-2026 the plan will be updated to describe how students, faculty and staff will be involved in plan development and implementation | Establish a cross-functional sustainability task force to develop and finalize a decarbonization plan that ensures involvement of students, faculty, and staff. (1) | Establish a cross-functional sustainability task force | VPBS / VPAA | 2024-2029 | VPBS
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | EWU will analyze faculty and staff turnover to develop, implement, and evaluate programs to improve recruitment and increase retention. (1,2) | Analyze faculty and staff turnover | VPBS/VPPC | 2025-2027 | VPBS
IIPP Outcome 2: Increase the recruitment of qualified applicants for all permanent EWU positions by 1% annually, and align employee demographics with the diversity of the EWU student population. | EWU will analyze faculty and staff turnover to develop, implement, and evaluate programs to improve recruitment and increase retention. (1,2) | Analyze faculty and staff turnover | VPBS/VPPC | 2025-2027 | VPBS
RA/RI Outcome 3: By 2025-2026, EWU will complete a comprehensive regional economic profile using data-driven analytics and use that profile to promote academic offerings that benefit our region in preparation for the development of an academic master plan. | EWU will develop a joint urban planning framework with Cheney and the West Plains to align campus development with regional growth, fostering professional partnerships and student opportunities. (3,6) | Develop a joint urban planning framework with Cheney and the West Plain | VPAA / VPBS / VPSA | 2025-2027 | VPBS
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | EWU will develop a joint urban planning framework with Cheney and the West Plains to align campus development with regional growth, fostering professional partnerships and student opportunities. (3,6) | Develop a joint urban planning framework with Cheney and the West Plain | VPAA / VPBS / VPSA | 2025-2027 | VPBS
IIPP Outcome 3: By 2025-2026, EWU will develop a campus master plan, which will explicitly incorporate residence halls, and include a vision for both Cheney and Spokane locations. | Develop robust residential life plan including physical structure, programs and assessment. (3) | Develop robust residential life plan | VPSA/VPBS | 2024-2029 | VPBS
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | Enhance faculty and staff well-being and resilience with a data-informed approach (1,4) | Enhance faculty and staff well-being | VPBS/VPAA | 2025-2027 | VPBS
IIPP Outcome 4: Overall campus Climate Survey score will increase by 10% in 2027-2028 and meet or exceed other peer and national institutions. | Enhance faculty and staff well-being and resilience with a data-informed approach (1,4) | Enhance faculty and staff well-being | VPBS/VPAA | 2025-2027 | VPBS
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPBS
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPBS
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPBS
SSE Outcome 4: By 2028-2029, decrease the DFW (Drop, Fail, and Withdrawal) rates in courses with historically high DFW rates and reduce the DFW rates for all courses to less than 20%. | Expand the use of Open Educational Resources (OER) to reduce costs and increase access to learning materials. (1,2,3,4) | Expand the use of Open Educational Resources (OER) | VPAA/VPBS | 2025-2027 | VPBS
IIPP Outcome 3: By 2025-2026, EWU will develop a campus master plan, which will explicitly incorporate residence halls, and include a vision for both Cheney and Spokane locations. | Our facilities and technology will support excellence in education and provide an intentional and predictable roadmap for development, remain flexible to respond to educational demands, strengthen our IT infrastructure, and become a model for other institutions. Incorporate campaign funds to enhance campus facilities and technological infrastructure, supporting excellence in education and fostering community integration. (3) | Support excellence in education by strengthening infrastructure | VPBS | 2024-2027 | VPBS

## Student Affairs
University Outcomes (Performance Target/Metric) | Activity | Activity *Short* Name | RESPONSIBILITY | TIMELINE | RESPONSIBLE_PARTY
Belonging Outcome 3: By 2026-2027, the number of students who participate in a university mentoring program or university support service will increase by 10% and participants will have a 10% greater outcome (measured by retention and graduation) than those who did not participate in a mentorship opportunity. | By the end of the 2027 academic year, EWU will establish a framework to effectively communicate, coordinate, support, track, and assess mentorship and university support service opportunities (3) | Assess mentorship and university support service opportunities | VPAA/VPSA | 2026-2028 | VPSA
SSE Outcome 3: By 2026-2027, develop a multi-dimensional model of well-being (e.g., financial well-being, academic well-being, etc.) that is integrated campus wide to improve the student positive mental health score as indicated in the Healthy Minds survey by 10% in five years. | Create a cross-divisional task force to develop and implement a Comprehensive Campus-Wide student Well-Being Program. (3) | Develop a comprehensive campus-wide student well-being program | VPSA | 2024-2027 | VPSA
RA/RI Outcome 3: By 2025-2026, EWU will complete a comprehensive regional economic profile using data-driven analytics and use that profile to promote academic offerings that benefit our region in preparation for the development of an academic master plan. | EWU will develop a joint urban planning framework with Cheney and the West Plains to align campus development with regional growth, fostering professional partnerships and student opportunities. (3,6) | Develop a joint urban planning framework with Cheney and the West Plain | VPAA / VPBS / VPSA | 2025-2027 | VPSA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | EWU will develop a joint urban planning framework with Cheney and the West Plains to align campus development with regional growth, fostering professional partnerships and student opportunities. (3,6) | Develop a joint urban planning framework with Cheney and the West Plain | VPAA / VPBS / VPSA | 2025-2027 | VPSA
IIPP Outcome 3: By 2025-2026, EWU will develop a campus master plan, which will explicitly incorporate residence halls, and include a vision for both Cheney and Spokane locations. | Develop robust residential life plan including physical structure, programs and assessment. (3) | Develop robust residential life plan | VPSA/VPBS | 2024-2029 | VPSA
RA/RI Outcome 4: By 2026-2027, 25% of the faculty will participate in community engagement activities, increasing to 75% by 2028-2029. | Enhance applied learning opportunities with specific fundraising for these student opportunities. (4,6,7) | Enhance applied learning opportunities | VPSA/VPUA | 2024-2027 | VPSA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | Enhance applied learning opportunities with specific fundraising for these student opportunities. (4,6,7) | Enhance applied learning opportunities | VPSA/VPUA | 2024-2027 | VPSA
RA/RI Outcome 7: By 2028-2029, EWU will develop a multi-year investment and change-management plan that coordinates major state and institutional infrastructure investments with the development of faculty, student, and community engagement programs. | Enhance applied learning opportunities with specific fundraising for these student opportunities. (4,6,7) | Enhance applied learning opportunities | VPSA/VPUA | 2024-2027 | VPSA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Establish an office of applied learning and community engagement to develop, coordinate, and promote internships, co-ops, service-learning, and undergraduate research in collaboration with academic departments, community partners, and employers. (1,2,5) | Establish an office of applied learning and community engagement | VPSA/VPAA | 2024-2027 | VPSA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Establish an office of applied learning and community engagement to develop, coordinate, and promote internships, co-ops, service-learning, and undergraduate research in collaboration with academic departments, community partners, and employers. (1,2,5) | Establish an office of applied learning and community engagement | VPSA/VPAA | 2024-2027 | VPSA
SSE Outcome 5: Incorporate in experiential learning opportunities (including practicum, internships, research projects, community engagement) in undergraduate degree curriculum, by cataloging current opportunities by the end of 2024-25 with 100% of programs reaching experiential learning integration by 2028-29. | Establish an office of applied learning and community engagement to develop, coordinate, and promote internships, co-ops, service-learning, and undergraduate research in collaboration with academic departments, community partners, and employers. (1,2,5) | Establish an office of applied learning and community engagement | VPSA/VPAA | 2024-2027 | VPSA
RA/RI Outcome 4: By 2026-2027, 25% of the faculty will participate in community engagement activities, increasing to 75% by 2028-2029. | Establish and/or strengthen programs and commitment to community engagement (e.g., applied learning, alumni and philanthropic engagement, etc.) (4,6,7) | Establish and/or strengthen programs and commitment to community engagement | VPAA/VPSA | 2024-2027 | VPSA
RA/RI Outcome 6: By 2026-2027, 75% of programs will have assessed alignment between program content, student learning outcomes, and regional skills needs; by 2029, 90% of programs will have completed such an assessment. | Establish and/or strengthen programs and commitment to community engagement (e.g., applied learning, alumni and philanthropic engagement, etc.) (4,6,7) | Establish and/or strengthen programs and commitment to community engagement | VPAA/VPSA | 2024-2027 | VPSA
RA/RI Outcome 7: By 2028-2029, EWU will develop a multi-year investment and change-management plan that coordinates major state and institutional infrastructure investments with the development of faculty, student, and community engagement programs. | Establish and/or strengthen programs and commitment to community engagement (e.g., applied learning, alumni and philanthropic engagement, etc.) (4,6,7) | Establish and/or strengthen programs and commitment to community engagement | VPAA/VPSA | 2024-2027 | VPSA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Implement targeted support programs and initiatives focused on academic, financial, and social resources specifically designed to address the unique challenges faced by historically marginalized student populations. (1,2) | Implement targeted support programs with a focus on historically marginalized populations | VPAA/VPSA | 2024-2026 | VPSA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Implement targeted support programs and initiatives focused on academic, financial, and social resources specifically designed to address the unique challenges faced by historically marginalized student populations. (1,2) | Implement targeted support programs with a focus on historically marginalized populations | VPAA/VPSA | 2024-2026 | VPSA
SSE Outcome 1: Annually increase first to second year retention rate by 1 percentage point, closing structural equity gaps for targeted student populations 1.5-3 percentage points, while growing new student enrollment by 0.5 percent and targeted student populations 1 percent. | Revamp First Year Experience, starting with strong pre-student programming, including New Student Orientation and Summer Bridge Programs. (1,2) | Revamp First Year Experience Programming | VPAA/VPSA | 2024-2026 | VPSA
SSE Outcome 2: Annually, increase overall graduation rate by 0.5 percentage points while closing structural equity gaps for targeted populations 1 percentage point. | Revamp First Year Experience, starting with strong pre-student programming, including New Student Orientation and Summer Bridge Programs. (1,2) | Revamp First Year Experience Programming | VPAA/VPSA | 2024-2026 | VPSA

## People and Culture
University Outcomes (Performance Target/Metric) | Activity | Activity *Short* Name | RESPONSIBILITY | TIMELINE | RESPONSIBLE_PARTY
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | Offer staff in service programs and an annual faculty retreat (1,5) | Offer staff in service programs and an annual faculty retreat | VPPC/VPAA | 2024-2029 | VPPC
IIPP Outcome 5: By 2026-2027, 100% of staff will participate in a professional development opportunity annually | Offer staff in service programs and an annual faculty retreat (1,5) | Offer staff in service programs and an annual faculty retreat | VPPC/VPAA | 2024-2029 | VPPC
Belonging Outcome 1: By 2025-2026, all university and academic policies, including those specific to individual units, will undergo an equity-minded audit to identify policies and practices contributing to inequitable outcomes for historically underrepresented students/faculty/staff. | Based on the audit findings, develop and implement comprehensive action plans to revise policies, promote inclusivity, and ensure equitable opportunities and outcomes for all students, faculty, and staff. (1,2) | Based on the audit findings, develop and implement comprehensive action plans | VPPC/ELT | 2026-2029 | VPPC
Belonging Outcome 2: By 2027-2028, all academic and student support units will implement equity-minded accountability and assessment practices and an annual reporting instrument that includes measures such as the participation and/or success rates of students disaggregated by race/ethnicity, socioeconomic status, and gender. | Based on the audit findings, develop and implement comprehensive action plans to revise policies, promote inclusivity, and ensure equitable opportunities and outcomes for all students, faculty, and staff. (1,2) | Based on the audit findings, develop and implement comprehensive action plans | VPPC/ELT | 2026-2029 | VPPC
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | EWU will create an onboarding and training program that ensures new employees and those in new roles are integrated, understand their unit's goals, and have immediate access to essential resources and tools. (1,4) | Create an improved onboarding and training program | VPPC | 2025-2029 | VPPC
IIPP Outcome 4: Overall campus Climate Survey score will increase by 10% in 2027-2028 and meet or exceed other peer and national institutions. | EWU will create an onboarding and training program that ensures new employees and those in new roles are integrated, understand their unit's goals, and have immediate access to essential resources and tools. (1,4) | Create an improved onboarding and training program | VPPC | 2025-2029 | VPPC
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | EWU will cultivate a community of practice that invests in a workplace culture that provides resources for the continuous learning and professional development of all employees. (1,5) | Cultivate a community of practice for the continuous learning and professional development of all employees | VPPC | 2024-2029 | VPPC
IIPP Outcome 5: By 2026-2027, 100% of staff will participate in a professional development opportunity annually | EWU will cultivate a community of practice that invests in a workplace culture that provides resources for the continuous learning and professional development of all employees. (1,5) | Cultivate a community of practice for the continuous learning and professional development of all employees | VPPC | 2024-2029 | VPPC
Belonging Outcome 5: By 2027-2028, all of EWU will have an improved sense of belonging by improved student journey mapping, onboarding, and training experiences to include surveys of satisfaction and exit interview feedback to increase sense of belonging for all. | Develop resources for university employees for successful onboarding and integration into university and community. (5) | Develop resources for successful onboarding | VPPC/President's Office | 2024-2025 | VPPC
Belonging Outcome 3: By 2026-2027, the number of students who participate in a university mentoring program or university support service will increase by 10% and participants will have a 10% greater outcome (measured by retention and graduation) than those who did not participate in a mentorship opportunity. | Implement online synchronous and asynchronous, as well as in-person opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning, while educating participants about co-curricular offerings available to students. (3,4) | Implement opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning | VPAA/VPPC/President's Office | 2024-2029 | VPPC
Belonging Outcome 4: By 2027-2028, 100% of faculty and staff will have participated in formal training opportunities to support their growth in culturally responsive teaching and learning support, emphasizing curricular and co-curricular learning spaces (e.g., Inclusive Teaching Academy). | Implement online synchronous and asynchronous, as well as in-person opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning, while educating participants about co-curricular offerings available to students. (3,4) | Implement opportunities that allow faculty and staff to grow in culturally responsive teaching and inclusive learning | VPAA/VPPC/President's Office | 2024-2029 | VPPC
IIPP Outcome 2: Increase the recruitment of qualified applicants for all permanent EWU positions by 1% annually, and align employee demographics with the diversity of the EWU student population. | Implement targeted recruitment initiatives that actively seek out qualified applicants from diverse backgrounds, and collaborate with diverse professional organizations to widen the pool of potential candidates. (2) | Implement targeted recruitment initiatives | VPPC | 2024-2029 | VPPC
Belonging Outcome 1: By 2025-2026, all university and academic policies, including those specific to individual units, will undergo an equity-minded audit to identify policies and practices contributing to inequitable outcomes for historically underrepresented students/faculty/staff. | Select a self-auditing process and offer training to unit-level participants. The audit process will be developed, trained, and monitored. (1,2) | Select a self-auditing process | VPPC | 2025-2028 | VPPC
Belonging Outcome 2: By 2027-2028, all academic and student support units will implement equity-minded accountability and assessment practices and an annual reporting instrument that includes measures such as the participation and/or success rates of students disaggregated by race/ethnicity, socioeconomic status, and gender. | Select a self-auditing process and offer training to unit-level participants. The audit process will be developed, trained, and monitored. (1,2) | Select a self-auditing process | VPPC | 2025-2028 | VPPC
IIPP Outcome 1: Increase retention of employees for all permanent EWU positions by 1 percentage point annually and targeted employees by 2.5 percentage points to reflect the EWU student population. | EWU will analyze faculty and staff turnover to develop, implement, and evaluate programs to improve recruitment and increase retention. (1,2) | Analyze faculty and staff turnover | VPBS/VPPC | 2025-2027 | VPPC
IIPP Outcome 2: Increase the recruitment of qualified applicants for all permanent EWU positions by 1% annually, and align employee demographics with the diversity of the EWU student population. | EWU will analyze faculty and staff turnover to develop, implement, and evaluate programs to improve recruitment and increase retention. (1,2) | Analyze faculty and staff turnover | VPBS/VPPC | 2025-2027 | VPPC